## Sheet1
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | Wireframes for all screens |  | High | 8 | Doing | - Meets acceptance criteria - Passes tests (linting, unit, integration, e2e) - Pushed to github and reviewed via Pull Request
2 | UML diagram of backend |  | High | 5 | Doing
3 | Coding of basic functionality for classes |  | High | 6 | Doing
4 | Login UI |  | High | 4 | Doing
5 | Login API Endpoint |  | High | 4 | Doing
6 | Registration (sign up) for each user - UI |  | High | 6 | Doing
7 | Registration Endpoint |  | High | 6 | Doing
8 | Write user stories |  | High | 10 | Doing
11 | As a business owner, I want to be able to log in so I can view my profile | Business Owner | High | 3 | Todo
12 | As a business owner, I want to be able to add a new employee so I have a record of new hires. | Business Owner | High | 3 | Todo |  | Next Sprint
13 | As a business owner, I want to be able to add working dates and times for the next month so I can provide customers with more options. | Business Owner | High | 2 | Todo
14 | As a business owner, I want to be able to edit working dates and times for the next month so I can ensure service times are up to date. | Business Owner | Medium | 1 | Todo
15 | As a business owner, I want to view a summary of past bookings so I can get an overview of bookings made. | Business Owner | Low | 1 | Todo |  | Next Sprint
16 | As a business owner, I want to view all workers' availability for the next 7 days so I can ensure that employee resources are being used effectively. | Business Owner | Low | 3 | Todo
17 | As a customer, I want to be able to log into and out of the system so I can access book a service when needed. | Customer | High | 3 | Todo
18 | As a customer, I want to be able to sign up to the system so that I can make a booking. | Customer | High | 3 | Todo |  | Next Sprint
19 | As a customer, I want to be able to access my dashboard so I may see my personal information. | Customer | High | 4 | Todo |  | Next Sprint
20 | As a customer, I want to be able to book a service so I can get the benefit of that service. | Customer | High | 3 | Todo |  | Next Sprint
21 | As a customer, I want to be able to cancel a booking so I can not receive that service when it is no longer needed. | Customer | High | 1 | Todo |  | Next Sprint
22 | As a customer, I want to be able to check availability information for services so I can make an informed decision. | Customer | Low | 1 | Todo
23 | As a customer, I want to be to see a history of past bookings so that I have a historical record. | Customer | Low | 4 | Todo |  | Next Sprint
24 | As a worker, I want to be able to log in and out so that I can see employee-only content. | Worker | High | 2 | Todo
25 | As a worker, I want to be able to see my assigned working hours on the profile page so that I have correct job information. | Worker | Medium | 4 | Todo
26 | As an administrator I want to be able to store user log in information so I may authenticate users | Administrator |  |  | Todo
27 | As a customer I want to receive an alert when a booking is approaching. | Customer | Low |  | Todo
28 | As a customer I want to be able to update the web page live to see the changes I have made | Customer | Medium |  | Todo
29 | As a business owner, I want to be able to upload details of my business so customers can more easily find me. | Business Owner | Medium |  | Todo
30 | As an administrator I want to be able to send bash/SQL commands to the SQL server to perform root tasks such as creating logins and modifying permissions | Administrator | High |  | Todo |  | Not sure if these should be on the product backlog as they don't provide value to the end users
31 | As an administrator I want to be able to send bash commands to the web server to test bugs, layouts, and server configurations | Administrator | High |  | Todo